## Sheet1
Defect ID | Description | Priority | Severity | Test ID | Status
1 | User login with empty username and empty password. | Medium | Low | 3.1.2.1 | Pending
2 | User login with correct username and empty password. | Medium | Low | 3.1.2.1 | Pending
3 | User updates their height with non-possible small value. | Low | Low | 3.1.2.3, 3.1.3.3, 3.1.4.3, 3.1.5.3 | Pending
4 | The user wants to update their height with non-possible values: number zero input. | Low | Low | 3.1.2.3, 3.1.3.3, 3.1.4.3, 3.1.5.3 | Pending
5 | The user wants to update their height with non-possible values: negative number input. | Low | Low | 3.1.2.3, 3.1.3.3, 3.1.4.3, 3.1.5.3 | Pending
6 | The user wants to update their weight with non-possible values: a number below 100 lbs input. | Low | Low | 3.1.2.3, 3.1.3.3, 3.1.4.3, 3.1.5.3 | Pending
7 | The user wants to update their weight with non-possible values: number zero input. | Low | Low | 3.1.2.3, 3.1.3.3, 3.1.4.3, 3.1.5.3 | Pending
8 | The user wants to update their weight with non-possible values: negative number input. | Low | Low | 3.1.2.3, 3.1.3.3, 3.1.4.3, 3.1.5.3 | Pending
9 | The user updates their profile picture with an invalid url (url does not end with extension .jpg, .jpeg, .gif, .png). | Low | Low | 3.1.2.3, 3.1.3.3, 3.1.4.3, 3.1.5.3 | Pending
10 | User can register with username that already exists and password | High | Low | 3.1.1.1 | Pending
11 | User can register with a blank username password | High | Low | 3.1.1.1 | Pending
12 | User can register with username and a blank password | High | Low | 3.1.1.1 | Pending
13 | User can register with a blank username and a blank password | High | Low | 3.1.1.1 | Pending
14 | Admin adds a season by typing nothing | Medium | Low | 3.1.4.11 | Pending
15 | Admin schedules a game series by inputting nothing and pressing schedule | High | Low | 3.1.4.12 | Pending
16 | Admin schedules a game series with no date selected | Medium | Low | 3.1.4.12 | Pending
17 | Admin schedules a game series with a past date selected | High | Low | 3.1.4.12 | Pending
18 | Admin schedules a game series with no sports selected | Medium | Low | 3.1.4.12 | Pending